## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 12 | Day 11 | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Walt Disney | Sekilas tentang Walt Disney | Task 1.1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Walt Disney | Sekilas tentang Walt Disney | Task 1.2 | 2 | 2 | 1 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Walt Disney | Masa Anak-anak | Task 1 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Walt Disney | Masa Remaja | Task 1 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Walt Disney | Awal mula Karir | Task 1.1 | 3 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Walt Disney | Awal mula Karir | Task 1.2 | 2 | 3 | 1 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Walt Disney | Laugh O'Gram Studio | Task 1 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Walt Disney | Hollywood | Task 1 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 1 | 0
Walt Disney | Zaman Keemasan Animasi | Task 1.1 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Walt Disney | Zaman Keemasan Animasi | Task 1.2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0
Walt Disney | Selama Perang Dunia II | Task 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 0 | 1 | 0
Walt Disney | Setelah Perang | Task 1 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 1 | 0 | 0 | 1 | 0
Walt Disney | Taman Bermain | Task 1 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 0 | 1 | 0
Walt Disney | Kehidupan Pribadi | Task 1 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 1 | 0
Walt Disney | Penghargaan | Task 1 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 1 | 0
Walt Disney | Edit Tampilan Presentasi | Task 1.1 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 0
Walt Disney | Edit Tampilan Presentasi | Task 1.2 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 8 | 8 | 0
Walt Disney | Edit Tampilan Presentasi | Task 1.3 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 8 | 8 | 3
Ideal - Remaining efforts in uninterrupted working hours |  |  | 54 | 49.5 | 45 | 40.5 | 36 | 31.5 | 27 | 22.5 | 18 | 13.5 | 9 | 4.5 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 54 | 53 | 48 | 51 | 40 | 41 | 39 | 36 | 26 | 25 | 27 | 32 | 3
Note on F5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on H5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on I5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered